## Status
Milestone | Phase | Phase Name | Deliverable | Timeframe | Phase Total | Status | Notes
Kickoff | Phase 0 | Initiation | Kickoff | Week 0 | 5000 | Completed | Main missing functionality is foreign exchanges. Need to do one to determine the level of effort and complexity of the api.
M1 | Phase 1 | MVP Build | UI/UX Mockups | Week 1 |  | Completed | Modern Flask web interface with responsive design implemented
M1 | Phase 1 | MVP Build | Watchlist management | Week 2-3 |  | Completed | Watchlist functionality implemented with persistent storage
M1 | Phase 1 | MVP Build | Top Movers display | Week 2-3 |  | Partially Completed - Missing Top 5 Gainers/Losers | Basic movers display implemented, but missing dedicated top 5 gainers/losers section
M1 | Phase 1 | MVP Build | Manual trade execution | Week 2-3 |  | Completed - Simulated trades only | Manual trade execution with simulated trades implemented, no real broker integration
M1 | Phase 1 | MVP Build | ECSE Regional Exchange | Week 3-4 | 9974.42 | Not Implemented | Support for Eastern Caribbean Securities Exchange (ECSE) regional exchange covering multiple countries not implemented
M2 | Phase 2 | Auto & Reporting | Real-time graph | Week 5-6 |  | Completed | Real-time graphing with WebSocket updates implemented
M2 | Phase 2 | Auto & Reporting | Auth & Rate Limiting | Week 6-7 |  | Partially Completed - Rate limiting issues with some APIs | Basic rate limiting implemented but some API rate limit issues persist
M2 | Phase 2 | Auto & Reporting | Internal QA + Deployment | Week 7-8 |  | Completed | Comprehensive logging system with web viewer implemented
M2 | Phase 2 | Auto & Reporting | Auto-trading logic | Week 2-3 |  | Completed - Simulated only | Auto-trading logic implemented but only for simulated trades
M2 | Phase 2 | Auto & Reporting | Financial ratios | Week 2-3 |  | Not Implemented - Missing detailed metric/fundamentals | Basic financial data available but missing detailed ratios and fundamentals
M2 | Phase 2 | Auto & Reporting | Reporting module | Week 4 |  | Partially Completed - Missing downloadable reports | Basic reporting available in UI but missing downloadable reports
M2 | Phase 2 | Auto & Reporting | CNBC-style UI | Not Implemented |  | Not Implemented | Standard Bootstrap UI implemented instead of CNBC-style UI
M2 | Phase 2 | Auto & Reporting | QA docs | Week 5-6 | 6649.61 | Completed | Comprehensive documentation and help sections implemented
M3 | Phase 3 | Intelligence | News integration | Week 1-2 |  | Completed - Multiple sources integrated | Multiple news sources integrated (Finnhub, Yahoo Finance, Alpha Vantage, Reddit)
M3 | Phase 3 | Intelligence | Earnings profiles | Week 1-2 |  | Completed - Missing company profiles | Basic earnings data available but missing detailed company profiles
M3 | Phase 3 | Intelligence | Ownership/options data | Week 3-4 |  | Not Implemented - Missing detailed ownership data | Basic options data available but missing detailed ownership information
M3 | Phase 3 | Intelligence | Alerts system | Week 5 |  | Completed - Telegram alerts implemented | Comprehensive Telegram alert system with configurable recipients implemented
M3 | Phase 3 | Intelligence | QA improvements | Week 6-8 | 7065.21 | Completed | Extensive error handling and validation implemented
M4 | Phase 4 | AI & Advanced | Mock trading | Week 1-2 |  | Completed | Simulated trading with portfolio tracking implemented
M4 | Phase 4 | AI & Advanced | Sentiment aggregation | Week 3-4 |  | Completed | Multi-source sentiment aggregation with AI processing implemented
M4 | Phase 4 | AI & Advanced | Voice trading | Week 5-6 |  | Not Implemented | Voice trading functionality not implemented
M4 | Phase 4 | AI & Advanced | AI back testing | Week 6-7 |  | Completed | AI backtesting with historical performance analysis implemented
M4 | Phase 4 | AI & Advanced | Transparency & Education | Week 8 | 9558.82 | Completed - Debug panel showing API requests/responses | System status page with detailed performance metrics implemented
M5 | Phase 5 | Final Delivery | Final QA release | Week 9-10 | 4156.01 | In Progress | System running but final QA and optimizations ongoing
TOTALS |  |  |  |  | 42404.07
Additional Features Not in Original Timeline
Category | Feature | Notes
Performance Optimization | PostgreSQL Cache System | Completed - 2,400x faster cached responses
Performance Optimization | Smart Batching & Concurrency | Completed - 5-10x performance improvement
Performance Optimization | WebSocket Real-time Updates | Completed - Live progress tracking
Performance Optimization | Thread Pool Optimization | Completed
Telegram Integration | Alert Notification System | Completed
Telegram Integration | Configurable Recipients | Completed
Telegram Integration | Telegram Integration | Completed
Enhanced AI Analysis | Multiple AI Provider Support | Completed - OpenAI GPT/Ollama/DeepSeek
Enhanced AI Analysis | Local AI Processing Options | Completed - Ollama local model support
System Monitoring | Performance Metrics Dashboard | Completed - Comprehensive system status page
System Monitoring | Cache Statistics | Completed - Detailed cache analytics
Trading Strategies | Multiple Strategy Types | Completed - Conservative/Moderate/Income-Focused
Trading Strategies | Risk Level Assessments | Completed - Risk assessment for different account sizes
Data Sources | Enhanced Reddit Integration | Completed - 30+ subreddits monitored
Data Sources | Multi-source News Aggregation | Completed - Finnhub, Yahoo Finance, Alpha Vantage, Reddit
User Experience | Theme Switching | Completed - Light/Dark mode support
User Experience | Responsive Design | Completed - Mobile-friendly interface
Logging System | Enhanced Logging | Completed - Comprehensive logging with web viewer
Documentation | Interactive Help | Completed - In-app help and documentation

## Sheet1
Phase Total
5000
9974.42
6649.61
7065.21
9558.82
4156.01
42404.07